## Sheet1
Index | Task | Detail | Start Time | End Time | Days | By
1 | Database design | ER Diagram | 2017-05-29 | 2017-06-09 | 10 | Janaka/Suranga
2 | User Login/Administration | User create Interface | 2017-06-12 | 2017-06-16 | 5 | Suranga
|  | User login control with specific roles | 2017-06-20 | 2017-06-27 | 5 | Suranga
3 | Agent/Broker/Bancassurance management process | Data Migration | 2017-06-28 | 2017-07-03 | 4 | Suranga
|  | Design Basic - Personal / Education / Other Details Form | 2017-06-12 | 2017-06-19 | 6 | Janaka
|  | Heirarchy Design with Group or Individual | 2017-06-20 | 2017-06-27 | 5 | Janaka | 30th June
5 | Commission calculation process | Commission Calculation Rate Chart - Normal(Agent / Broker / HNB etc...) | 2017-06-28 | 2017-07-10 | 10 | Janaka
|  | Commission Calculation Rate Chart - Alternative Channel | 2017-07-11 | 2017-07-18 | 6 | Janaka
|  | Commission Calculation Rate Chart - Overriding | 2017-07-19 | 2017-07-25 | 5 | janaka
|  | Interface Design for Refund & Cancellation | 2017-07-04 | 2017-07-11 | 5 | janaka
|  | Manual DPTS upload interface | 2017-07-12 | 2017-07-14 | 3 | janaka
|  | Commission Calculation process | 2017-07-17 | 2017-08-04 | 14 | suranga
|  | OR commission Calculation process | 2017-08-08 | 2017-08-25 | 14 | Suranga
|  | Accrued commission Calculation process | 2017-08-28 | 2017-09-18 | 14 | Suranga
6 | Bancassurance Incentive Process | Keep Incentive percentage and calculate base on achivement range (Ex:Achivement 80%-100% --> Incentive 1%) |  |  | 8
7 | Feild staff Incentive Process | Incentive - Individual (Advisor/S.Advisor/FC/SFC/AFSM/FSM/SFSM)
|  | 01. FST Allowance | 2017-07-26 | 2017-08-10 | 10 | Janaka
|  | 02. Target Allowance | 2017-08-11 | 2017-08-24 | 10 | Janaka
Bonus - Group (Advisor/S.Advisor/FE/SFE/AFM/FM/AGFM/GFM/SGFM)
|  | 01. Retainer Allowance | 2017-08-25 | 2017-09-07 | 8 | Janaka
|  | 02. Retainer Bonus Allowance | 2017-09-08 | 2017-09-14 | 5 | Janaka
|  | 03. Retainer Arrears | 2017-09-15 | 2017-09-21 | 5 | Janaka
|  | 04. Advisor Development Allowance | 2017-09-22 | 2017-09-28 | 5 | Janaka
|  | 05. Group Achivement | 2017-09-29 | 2017-10-09 | 8 | Janaka
4 | Data Collection for comission calculation | PID Data migration (Opening balance from Biscoa) | 2017-09-19 | 2017-09-26 | 6 | Suranga
|  | TCS Receipt upload (TCS product & Non TCS product | 2017-09-27 | 2017-10-30 | 4 | Suranga
|  | Manual receipt Upload (Dollor Receipt) | 2017-10-31 | 2017-11-06 | 3 | Suranga
|  | Income transfer (TCS sys vouchers) | 2017-11-07 | 2017-11-24 | 14 | Suranga
|  | Non TCS - Manually upload DPTS details -MRP /MCR / PWR / TAKAFUL / INVESTMENT / MY FREEDOM / MY PENSION | 2017-11-27 | 2017-11-30 | 4 | Suranga
|  | Refunds / Cancellations / Cheque Returns Utilize | 2017-12-04 | 2017-12-15 | 10 | Suranga/Janaka
|  |  | 2017-12-18 | 2017-12-22 | 5 | Suranga
8 | Report Designs | Servicing unit reports List - (Date Range) |  |  |  | MIS
01. Commission Admin Expense GWP NON BAC
02. Commission Admin Expense GWP BAC
03. Cheque Returns Report
04. Refund Report
05. Main Data Base Report
06. Main Data TME
07. PID Life
08. NONBAC Advisor Commission statement
09. TME Commission Statement
10. Transfer Summery
11. BAC Advisor commission statement
12. Opening Balance Statement
13. Refund / Cheque Return Schedule
|  | Distribution Reports List |  |  |  | MIS
01. Advisor Direct team report
02. Advisor Group team report
03. Advisor main report
04. Advisor report with date range
05. Policy report with date range (Branch MIS)
06. Mobile numbers List
07. Title Mr./Mrs.- List from Gender
08. Stop commission reason List
09. Termination reason List
10. Black list details List
11. Recoveries List
12. Preference Language
|  | UAT Application & DB Environment |  |  | 2
|  | Application UAT Testing |  |  | 10
|  | Parallel Run |  |  | 90
|  | Live Hosting & Setup |  |  | 3

## Sheet2
Index | Task | Detail | Start Time | End Time | Days | By
1 | Database design | ER Diagram | 2017-05-29 | 2017-06-09 | 10 | Janaka/Suranga
2 | User Login/Administration | User create Interface | 2017-06-12 | 2017-06-16 | 5 | Suranga
|  | User login control with specific roles | 2017-06-20 | 2017-06-27 | 5 | Suranga
3 | Agent/Broker/Bancassurance management process | Data Migration | 2017-06-28 | 2017-07-03 | 4 | Suranga
|  | Design Basic - Personal / Education / Other Details Form | 2017-06-12 | 2017-06-19 | 6 | Janaka
|  | Heirarchy Design with Group or Individual | 2017-06-20 | 2017-06-27 | 5 | Janaka |  |  |  | Release Date
4 | Data Collection for comission calculation | PID with All tables Data migration (Opening balance from Biscoa) | 2017-09-19 | 2017-09-26 | 3 | Suranga |  | 2017-12-15 | 2017-12-19
|  | TCS Receipt upload (TCS product & Non TCS product | 2017-09-27 | 2017-10-30 | 5 | Suranga | DB Unit | 2017-12-20 | 2017-12-27
|  | Manual receipt Upload (Dollor Receipt-10.12 bis_ho) | 2017-10-31 | 2017-11-06 | 2 | Suranga |  | 2017-12-28 | 2017-12-29
|  | Non TCS - Manually upload DPTS details -MRP /MCR /GLP (check from where) | 2017-11-27 | 2017-11-30 | 4 | Suranga |  | 2018-01-02 | 2018-01-05
|  | Refunds / Cancellations / Cheque Returns Utilize(daily transfer to temp table) | 2017-12-04 | 2017-12-15 | 7 | Suranga |  | 2018-01-08 | 2018-01-16
|  | Income transfer (TCS sys vouchers only (+) values) | 2017-11-07 | 2017-11-24 | 7 | Suranga | DB Unit | 2018-01-17 | 2018-01-25
|  | Unit Testing and Error correction |  |  | 3 | Suranga |  | 2018-01-26 | 2008-01-30
|  | Release Date | [7 empty] | Release Date | 2017-01-30
5 | Commission calculation process | Commission Calculation Rate Chart - Normal(Agent / Broker / HNB etc...) | 2017-06-28 | 2017-07-10 | 10 | Janaka |  | 2017-12-08 | 2017-12-21
|  | Commission Calculation Rate Chart - Alternative Channel | 2017-07-11 | 2017-07-18 | 6 | Janaka |  | 2018-12-22 | 2018-01-03
|  | Commission Calculation Rate Chart - Overriding | 2017-07-19 | 2017-07-25 | 5 | janaka |  | 2018-01-04 | 2018-01-10
|  | Interface Design for Refund , Cheque Returns & Cancellation | 2017-07-04 | 2017-07-11 | 3 | janaka |  | 2018-01-11 | 2018-01-15
|  | Manual DPTS upload interface(confirmation from Life) | 2017-07-12 | 2017-07-14 | 3 | janaka |  | 2018-01-16 | 2018-01-18
|  | Commission Calculation process | 2017-07-17 | 2017-08-04 | 3 | suranga |  | 2018-02-01 | 2018-02-05
|  | OR commission Calculation process | 2017-08-08 | 2017-08-25 | 5 | suranga |  | 2018-02-06 | 2018-02-12
|  | Accrued commission Calculation process | 2017-08-28 | 2017-09-18 | 10 | Janaka |  | 2018-01-19 | 2018-02-02
|  | Unit Testing and Error correction / Reports |  |  | 11 | Suranga / Janaka |  | 2018-02-13 | 2017-02-28
|  | Release Date | [7 empty] | Release Date | 2017-02-28
6 | Bancassurance Incentive Process | Keep Incentive percentage and calculate base on achivement range (Ex:Achivement 80%-100% --> Incentive 1%) |  |  | 8 | Suranga |  | 2018-03-02 | 2018-03-13
(Upload interface for sales force table) - commission & Incentive both shoud follow the bank
7 | Feild staff Incentive Process | Incentive - Individual (Advisor/S.Advisor/FC/SFC/AFSM/FSM/SFSM)
|  | 01. FST Allowance | 2017-07-26 | 2017-08-10 | 10 | Janaka |  | 2018-02-19 | 2018-03-05
|  | 02. Target Allowance | 2017-08-11 | 2017-08-24 | 10 | Janaka |  | 2018-03-06 | 2018-03-19
Bonus - Group (Advisor/S.Advisor/FE/SFE/AFM/FM/AGFM/GFM/SGFM)
|  | 01. Retainer Allowance | 2017-08-25 | 2017-09-07 | 8 | suranga |  | 2018-03-14 | 2018-03-23
|  | 02. Retainer Bonus Allowance | 2017-09-08 | 2017-09-14 | 5 | suranga |  | 2018-03-26 | 2018-04-02
|  | 03. Retainer Arrears | 2017-09-15 | 2017-09-21 | 5 | Janaka |  | 2018-03-20 | 2018-03-26
|  | 04. Advisor Development Allowance | 2017-09-22 | 2017-09-28 | 5 | Janaka |  | 2018-03-27 | 2018-04-03
|  | 05. Group Achivement | 2017-09-29 | 2017-10-09 | 8 | suranga |  | 2018-04-03 | 2018-04-12
|  | Unit Testing and Error correction Reports |  |  | 10 | Suranga / Janaka
|  | Release Date | [7 empty] | Release Date | 2017-04-30
8 | Report Designs | Servicing unit reports List - (Date Range) |  |  |  | MIS
01. Commission Admin Expense GWP NON BAC
02. Commission Admin Expense GWP BAC
03. Cheque Returns Report
04. Refund Report
05. Main Data Base Report
06. Main Data TME
07. PID Life
08. NONBAC Advisor Commission statement
09. TME Commission Statement
10. Transfer Summery
11. BAC Advisor commission statement
12. Opening Balance Statement
13. Refund / Cheque Return Schedule
|  | Distribution Reports List |  |  |  | MIS
01. Advisor Direct team report
02. Advisor Group team report
03. Advisor main report
04. Advisor report with date range
05. Policy report with date range (Branch MIS)
06. Mobile numbers List
07. Title Mr./Mrs.- List from Gender
08. Stop commission reason List
09. Termination reason List
10. Black list details List
11. Recoveries List
|  | 12. Preference Language | [7 empty] | 9th Feb 2018 for All Queries
|  | UAT Application & DB Environment |  |  | 2
|  | Application UAT Testing |  |  | 10
|  | Parallel Run |  |  | 90
|  | Live Hosting & Setup |  |  | 3