## Sheet1
Database design | ER Diagram | S/J | 10 days | 2017-05-29 08:00 | 2017-06-09 17:00
User Login/Administration | User create Interface | S | 5 days | 2017-06-12 08:00 | 2017-06-16 17:00
| User login control with specific roles | S | 5 days | 2017-06-19 08:00 | 2017-06-23 17:00
Agent/Broker/Bancassurance management process | Data Migration | S | 4 days | 2017-06-27 08:00 | 2017-06-30 17:00
| Design Basic - Personal / Education / Other Details Form | J | 6 days | 2017-06-12 08:00 | 2017-06-19 17:00
| Heirarchy Design with Group or Individual | J | 6 days | 2017-06-20 08:00 | 2017-06-27 17:00
Data Collection for comission calculation | PID Data migration (Opening balance from Biscoa) - Have to consider two three tables | S | 6 days | 2017-07-03 08:00 | 2017-07-10 17:00
| TCS Receipt upload (TCS product & Non TCS product) | S | 4 days | 2017-07-11 08:00 | 2017-07-14 17:00
| Manual receipt Upload (Dollor Receipt) - study the process and try to take | J | 3 days | 2017-06-28 08:00 | 2017-06-30 17:00
| Income transfer (TCS sys vouchers) | S | 14 days | 2017-07-17 08:00 | 2017-08-03 17:00
| Non TCS - Manually upload DPTS details -MRP /MCR / PWR(TCS) / TAKAFUL / MY FREEDOM / MY PENSION | J | 4 days | 2017-07-03 08:00 | 2017-07-06 17:00
| Refunds / Cancellations / Cheque Returns Utilize | J | 10 days | 2017-07-07 08:00 | 2017-07-20 17:00
Commission calculation process | Commission Calculation Rate Chart - Normal(Agent / Broker / HNB etc...) | J | 10 days | 2017-07-21 08:00 | 2017-08-03 17:00
| Commission Calculation Rate Chart - Alternative Channel | J | 6 days | 2017-08-04 08:00 | 2017-08-11 17:00
| Commission Calculation Rate Chart - Overriding | J | 5 days | 2017-08-14 08:00 | 2017-08-18 17:00
| Interface Design for Refund & Cancellation | S | 5 days | 2017-08-04 08:00 | 2017-08-10 17:00
| Manual DPTS upload interface | S | 3 days | 2017-08-11 08:00 | 2017-08-15 17:00
| Commission Calculation process | S | 10 days | 2017-08-16 08:00 | 2017-08-29 17:00
| OR commission Calculation process | J | 5 days | 2017-08-21 08:00 | 2017-08-25 17:00
| Accrued commission Calculation process | J | 5 days | 2017-08-28 08:00 | 2017-09-01 17:00
Commission module testing with reports |  | J/S | 20 days? | 2017-09-04 08:00 | 2017-09-29 17:00
Bancassurance Incentive Process | Keep Incentive percentage and calculate base on achivement range (Ex:Achivement 80%-100% --> Incentive 1%) / (Upload interface for sales force table) - commission & Incentive both shoud follow the bank | S | 8 days | 2017-10-02 08:00 | 2017-10-11 17:00
Field staff Incentive Process(Incentive - Individual (Advisor/S.Advisor/FC/SFC/AFSM/FSM/SFSM)) | FST Allowance (With rule interfaces) | S | 10 days | 2017-10-12 08:00 | 2017-10-25 17:00
| Target Allowance (With rule interfaces) | J | 10 days | 2017-10-02 08:00 | 2017-10-13 17:00
Bonus - Group (Advisor/S.Advisor/FE/SFE/AFM/FM/AGFM/GFM/SGFM) | Retainer Allowance | J | 8 days | 2017-10-16 08:00 | 2017-10-25 17:00
| Retainer Bonus Allowance | J | 5 days | 2017-10-26 08:00 | 2017-11-01 17:00
| Retainer Arrears | J | 5 days | 2017-11-02 08:00 | 2017-11-08 17:00
| Advisor Development Allowance | S | 5 days | 2017-10-26 08:00 | 2017-11-01 17:00
| Group Achivement | S | 8 days | 2017-11-02 08:00 | 2017-11-13 17:00
Incentive module testing with reports |  | S/J | 10 days | 2017-11-14 08:00 | 2017-11-27 17:00
Report Designs (Servicing unit reports List - (Date Range)) | Commission Admin Expense GWP NON BAC |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Commission Admin Expense GWP BAC |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Cheque Returns Report |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Refund Report |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Main Data Base Report |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Main Data TME |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| PID Life |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| NONBAC Advisor Commission statement |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| TME Commission Statement |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Transfer Summery |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| BAC Advisor commission statement |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Opening Balance Statement |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Refund / Cheque Return Schedule |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
Distribution Reports List (Distribution Reports List) | Advisor Direct team report |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Advisor Group team report |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Advisor main report |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Advisor report with date range |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Policy report with date range (Branch MIS) |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Mobile numbers List |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Title Mr./Mrs.- List from Gender |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Stop commission reason List |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Termination reason List |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Black list details List |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Recoveries List |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
| Preference Language |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
UAT Application & DB Environment |  |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
Application UAT Testing |  |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
Parallel Run |  |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00
Live Hosting & Setup |  |  | 1 day? | 2017-06-06 08:00 | 2017-06-06 17:00